## Sheet1
|  |  | EARLY START | DURATION | EARLY FINISH
|  |  | 5 | 7 | 12
C
EARLY START | DURATION | EARLY FINISH | 5 | 0 | 12 | EARLY START | DURATION | EARLY FINISH
0 | 5 | 5 | LATE START | FLOAT | LATE FINISH | 12 | 6 | 18
| A | [5 empty] | F
0 | 0 | 5 | EARLY START | DURATION | EARLY FINISH | 12 | 0 | 18
LATE START | FLOAT | LATE FINISH | 5 | 3 | 8 | LATE START | FLOAT | LATE FINISH
D
|  |  | 5 | 0 | 8 | EARLY START | DURATION | EARLY FINISH | EARLY START | DURATION | EARLY FINISH
|  |  | LATE START | FLOAT | LATE FINISH | 8 | 3 | 11 | 11 | 4 | 15
[7 empty] | G |  |  | J
[6 empty] | 8 | 0 | 11 | 11 | 0 | 15 | EARLY START | DURATION | EARLY FINISH | EARLY START | DURATION | EARLY FINISH
[6 empty] | LATE START | FLOAT | LATE FINISH | LATE START | FLOAT | LATE FINISH | 15 | 4 | 19 | 19 | 12 | 31
[13 empty] | K |  |  | M
EARLY START | DURATION | EARLY FINISH | EARLY START | DURATION | EARLY FINISH | EARLY START | DURATION | EARLY FINISH |  |  |  | 15 | 0 | 19 | 19 | 0 | 31
0 | 5 | 5 | 5 | 2 | 7 | 7 | 7 | 14 |  |  |  | LATE START | FLOAT | LATE FINISH | LATE START | FLOAT | LATE FINISH
| B |  |  | E |  |  | H | [10 empty] | EARLY START | DURATION | EARLY FINISH | EARLY START | DURATION | EARLY FINISH
1 | 1 | 6 | 6 | 1 | 8 | 8 | 1 | 15 |  |  |  | EARLY START | DURATION | EARLY FINISH |  |  |  | 31 | 8 | 39 | 39 | 8 | 47
LATE START | FLOAT | LATE FINISH | LATE START | FLOAT | LATE FINISH | LATE START | FLOAT | LATE FINISH |  |  |  | 15 | 8 | 23 |  |  |  |  | N |  |  | P
[13 empty] | L |  |  |  |  | 31 | 0 | 39 | 39 | 0 | 47
[6 empty] | EARLY START | DURATION | EARLY FINISH |  |  |  | 23 | 8 | 31 |  |  |  | LATE START | FLOAT | LATE FINISH | LATE START | FLOAT | LATE FINISH
[6 empty] | 7 | 6 | 13 |  |  |  | LATE START | FLOAT | LATE FINISH
[7 empty] | I | [10 empty] | EARLY START | DURATION | EARLY FINISH |  |  |  | EARLY START | DURATION | EARLY FINISH
[6 empty] | 17 | 10 | 23 | [9 empty] | 23 | 4 | 27 |  |  |  | 47 | 4 | 51
[6 empty] | LATE START | FLOAT | LATE FINISH | [10 empty] | O | [5 empty] | Q
[18 empty] | 43 | 20 | 47 |  |  |  | 47 | 0 | 51
[18 empty] | LATE START | FLOAT | LATE FINISH |  |  |  | LATE START | FLOAT | LATE FINISH
float=late finish -early finish
late start= late finish-duration
critical path